Methodology

The project follows the Waterfall (System Development Life Cycle - SDLC) methodology. The project is divided into four sequential phases, and each phase must be completed and approved before the next one starts. This matches the time estimation of the project (15% / 20% / 35% / 30%).

| Phase | Main activities | Deliverables |
| --- | --- | --- |
| 1. Planning | Project identification, system request, feasibility study, time estimation, task identification, PERT and Gantt charts | Project plan |
| 2. Analysis | Interviews, questionnaire, DFDs, data dictionary, process specification, normalization, ERD, UML diagrams | Project proposal (requirements) |
| 3. Design | Architecture design, data storage design, program design, interface design | Project specification |
| 4. Implementation | Coding, testing, deployment, user training and maintenance | New system |

Why Waterfall was chosen

The requirements of a journal peer-review process are clear and stable (submit, assign, review, decide), so they can be defined completely at the beginning.

The course and the deadline (1 January) require clear phases and documents (plan, proposal, specification) at the end of each phase.

The team is small and works on a fixed schedule, so a simple and well-documented process is easier to manage.

Comparison with other methodologies

| Methodology | Advantages | Disadvantages | Decision |
| --- | --- | --- | --- |
| Waterfall | Simple; clear phases and documents; easy to manage and track | Hard to change requirements after a phase is finished | Selected |
| Agile (Scrum) | Flexible; frequent delivery; fast feedback | Needs continuous user involvement; less documentation | Not selected |
| Prototyping | Users see the interface early; fewer misunderstandings | Can take more time; risk of unclear scope | Used only for the interface prototypes |

Time Estimation

|  | Planning | Analysis | Design | Implementation |
| --- | --- | --- | --- | --- |
| Standard percentages | 15% | 20% | 35% | 30% |
| Estimated time based on planning time | Actual: 11 days | 15 days | 26 days | 22 days |

Total project duration: 74 days (11 October 2026 - 23 December 2026), ready before the 1 January deadline.

Tasks Identification

| Name of Task | System Request |
| --- | --- |
| Start Date | 11/10/2026 |
| End Date | 14/10/2026 |
| Person assigned to task | Member 1, Member 2 |
| Priority | High |
| Resources Needed | Microsoft Word |
| Estimated Time | 6 hours |
| Actual Time | 5 hours |

| Name of Task | Feasibility Study |
| --- | --- |
| Start Date | 15/10/2026 |
| End Date | 18/10/2026 |
| Person assigned to task | Member 3 |
| Priority | High |
| Resources Needed | Microsoft Word, Excel |
| Estimated Time | 8 hours |
| Actual Time | 7 hours |

| Name of Task | PERT Chart, Gantt Chart |
| --- | --- |
| Start Date | 19/10/2026 |
| End Date | 21/10/2026 |
| Person assigned to task | Member 4 |
| Priority | High |
| Resources Needed | MS Project |
| Estimated Time | 9 hours |
| Actual Time | 8 hours |

| Name of Task | Interview |
| --- | --- |
| Start Date | 22/10/2026 |
| End Date | 26/10/2026 |
| Person assigned to task | Member 1, Member 2 |
| Priority | Medium |
| Resources Needed | Microsoft Word |
| Estimated Time | 12 hours |
| Actual Time | 10 hours |

| Name of Task | Questionnaire |
| --- | --- |
| Start Date | 22/10/2026 |
| End Date | 25/10/2026 |
| Person assigned to task | Member 5 |
| Priority | Medium |
| Resources Needed | Google Forms |
| Estimated Time | 5 hours |
| Actual Time | 4 hours |

| Name of Task | Data Flow Diagram |
| --- | --- |
| Start Date | 27/10/2026 |
| End Date | 31/10/2026 |
| Person assigned to task | Member 3, Member 4 |
| Priority | High |
| Resources Needed | Draw.io / Internet |
| Estimated Time | 2 days |
| Actual Time | 14 hours |

| Name of Task | Data Store / Data Dictionary |
| --- | --- |
| Start Date | 1/11/2026 |
| End Date | 3/11/2026 |
| Person assigned to task | Member 3 |
| Priority | High |
| Resources Needed | Microsoft Word |
| Estimated Time | 1 day |
| Actual Time | 8 hours |

| Name of Task | Process Specification |
| --- | --- |
| Start Date | 1/11/2026 |
| End Date | 5/11/2026 |
| Person assigned to task | Member 1 |
| Priority | High |
| Resources Needed | Microsoft Word |
| Estimated Time | 2 days |
| Actual Time | 14 hours |

| Name of Task | Entity Relationship & Normalization |
| --- | --- |
| Start Date | 2/11/2026 |
| End Date | 5/11/2026 |
| Person assigned to task | Member 2 |
| Priority | High |
| Resources Needed | StarUML, MySQL Workbench |
| Estimated Time | 2 days |
| Actual Time | 12 hours |

| Name of Task | UML (Use Case, Class, Sequence) |
| --- | --- |
| Start Date | 2/11/2026 |
| End Date | 5/11/2026 |
| Person assigned to task | Member 5 |
| Priority | High |
| Resources Needed | StarUML |
| Estimated Time | 2 days |
| Actual Time | 13 hours |

| Name of Task | Architecture Design |
| --- | --- |
| Start Date | 6/11/2026 |
| End Date | 11/11/2026 |
| Person assigned to task | Member 4 |
| Priority | High |
| Resources Needed | Microsoft Word |
| Estimated Time | 3 days |
| Actual Time | 2 days |

| Name of Task | Data Storage Design |
| --- | --- |
| Start Date | 12/11/2026 |
| End Date | 16/11/2026 |
| Person assigned to task | Member 2 |
| Priority | High |
| Resources Needed | MySQL Workbench |
| Estimated Time | 3 days |
| Actual Time | 2 days |

| Name of Task | Program Design |
| --- | --- |
| Start Date | 17/11/2026 |
| End Date | 22/11/2026 |
| Person assigned to task | Member 3 |
| Priority | High |
| Resources Needed | Draw.io |
| Estimated Time | 3 days |
| Actual Time | 2 days |

| Name of Task | Interface Design |
| --- | --- |
| Start Date | 23/11/2026 |
| End Date | 1/12/2026 |
| Person assigned to task | Member 4, Member 5 |
| Priority | High |
| Resources Needed | Figma / Balsamiq |
| Estimated Time | 6 days |
| Actual Time | 5 days |

| Name of Task | Implementation (Coding) |
| --- | --- |
| Start Date | 2/12/2026 |
| End Date | 15/12/2026 |
| Person assigned to task | All members |
| Priority | High |
| Resources Needed | Visual Studio Code, MySQL |
| Estimated Time | 10 days |
| Actual Time | 9 days |

| Name of Task | Testing |
| --- | --- |
| Start Date | 16/12/2026 |
| End Date | 20/12/2026 |
| Person assigned to task | Member 1, Member 3 |
| Priority | High |
| Resources Needed | Browser, Postman |
| Estimated Time | 4 days |
| Actual Time | 3 days |

| Name of Task | Deployment & Documentation |
| --- | --- |
| Start Date | 21/12/2026 |
| End Date | 23/12/2026 |
| Person assigned to task | Member 2, Member 5 |
| Priority | Medium |
| Resources Needed | Web hosting |
| Estimated Time | 2 days |
| Actual Time | 2 days |

Pert Chart (MS-Project)

Critical path: A - B - C - D - F - H - K - L - M - N - O - P - Q  (74 days). Red boxes are critical activities (slack = 0); blue boxes have slack (E = 1, G = 2, I = 1, J = 1).

Gantt chart (MS-Project)